## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Milestone - 1
1 | 1 |  | Data Collection from multi-source enterprise systems such as Unstructured Data(Documents,Emails ,Reports ), Semi-Structured Data(Spreadsheets, Forms, CRM exports), & Structured Data(ERP, CRM, HRMS tables). |  |  |  | 3- Completed
2 | 2 |  | Data Cleaning & Data Ingestion code |  | 1 |  | 3- Completed
Milestone - 2
3 | 3 |  | Entity Extraction using spaCy (NER) |  | 2 |  | 3- Completed
4 | 4 |  | Relationship extraction using rule baesd method |  | 3 |  | 3- Completed
5 | 5 |  | Triple creation like (entity-relation-entity) |  | 4 |  | 3- Completed
6 | 6 |  | Knowledge Graph Construction using Neo4j graph database |  | 5 |  | 3- Completed
7 | 7 |  | Validate the graph |  | 6 |  | 3- Completed
Milestone - 3
8 | 8 |  | Embedding generation pipeline (to convert text into numeric value) following process like preprocessing, chunking and more. |  | 7 |  | 3- Completed
9 | 9 |  | Use FAISS vector database to store data |  | 8 |  | 3- Completed
10 | 10 |  | semantic search implementation |  | 9 |  | 3- Completed
11 | 11 |  | Rag based contextual Q&A |  | 10 |  | 3- Completed
12 | 12 |  | Evalution metrics & Report |  | 11 |  | 3- Completed
Milestone - 4
13 | 13 |  | We have to create a UI like a chatbot where I give query as input and chatbot give valid answer and also give performance metric like latency , rsponse time & source path using streamlit, Ollma LLM |  | 12 |  | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7